## Sheet1
Task Name | Duration | Notify To | Notify By Email | Notify By SMS | Is Optional | stage | owner
Upload Floor Plan | 48 | community_manager | TRUE | FALSE | FALSE | pre bid | designer
Upload Requirement Sheet | 48 |  | FALSE | FALSE | FALSE | pre bid | designer
Site Visit | 1 |  | FALSE | FALSE | TRUE | pre bid | designer
EC Visit | 1 |  | FALSE | FALSE | TRUE | pre bid | designer
Create Initial BOQ | 144 |  | FALSE | FALSE | FALSE | 10 % | designer
Custom Elements Feasibility | 1 | designer | TRUE | FALSE | TRUE | 10 % | designer
Custom Elements Estimation | 24 | designer | TRUE | FALSE | TRUE | 10 % | category
Client PPT | 24 |  | FALSE | FALSE | TRUE | 10 % | designer
Create Proposal | 144 | community_manager,designer | TRUE | FALSE | FALSE | 10 % | designer
Discount Proposal | 1 | community_manager,designer | TRUE | TRUE | TRUE | 10 % | designer
Discount Approval | 24 | community_manager,designer | TRUE | TRUE | TRUE | 10 % | community_manager
Proposal Sharing | 48 | community_manager,designer | TRUE | FALSE | FALSE | 10 % | designer
Client Approval | 96 | community_manager,designer | TRUE | FALSE | FALSE | 10 % | customer
Scope Checklist | 24 |  | FALSE | FALSE | FALSE | 10 % | designer
Booking form | 24 |  | FALSE | TRUE | TRUE | 10 % | designer
Payment Addition | 48 | community_manager,finance,business_head | TRUE | FALSE | FALSE | 10 % | designer
Payment Verification | 24 | community_manager,finance,business_head | TRUE | FALSE | FALSE | 10 % | finance
CM Approval for less than 10% Payment | 24 | community_manager,finance,business_head | TRUE | FALSE | TRUE | 10 % | community_manager
Request site measurement | 6 | community_manager | TRUE | FALSE | TRUE | 10% - 40% | designer
Assign SS for site measurement | 24 |  | FALSE | FALSE | TRUE | 10% - 40% | community_manager
upload measurements | 24 | community_manager,designer | TRUE | FALSE | TRUE | 10% - 40% | sitesupervisor
Create Final BOQ | 144 |  | FALSE | FALSE | FALSE | 10% - 40% | designer
Custom Elements Feasibility | 1 | designer | TRUE | FALSE | TRUE | 10% - 40% | designer
Custom Elements Estimation | 24 | designer | TRUE | FALSE | TRUE | 10% - 40% | category
Client final PPT with 3D render | 24 |  | FALSE | FALSE | TRUE | 10% - 40% | designer
Create Proposal | 144 | community_manager,designer | TRUE | FALSE | FALSE | 10% - 40% | designer
Discount Proposal | 1 | community_manager,designer | TRUE | FALSE | TRUE | 10% - 40% | designer
Discount Approval | 24 | community_manager,designer | TRUE | FALSE | TRUE | 10% - 40% | community_manager
Upload CAD files | 48 |  | FALSE | FALSE | TRUE | 10% - 40% | cad
Approve Final BOQ by CM | 48 | designer | TRUE | FALSE | TRUE | 10% - 40% | community_manager
Approve Final BOQ by Category | 48 | community_manager,designer | TRUE | FALSE | TRUE | 10% - 40% | category
Proposal Sharing | 48 | community_manager,designer | TRUE | FALSE | FALSE | 10% - 40% | designer
Client Approval | 96 | community_manager,designer | TRUE | FALSE | FALSE | 10% - 40% | customer
Payment Addition | 48 | community_manager,finance,business_head | TRUE | FALSE | FALSE | 10% - 40% | designer
Payment Verification | 24 | community_manager,finance,business_head | TRUE | FALSE | FALSE | 10% - 40% | finance
CM Approval for less than 40% Payment | 24 | community_manager,finance,business_head | TRUE | FALSE | TRUE | 10% - 40% | community_manager
SLI Creation | 24 | business_head | TRUE | FALSE | FALSE | 50 %
Vendor Selection | 48 | business_head | TRUE | FALSE | FALSE | 50 %
Create Purchase Order | 24 | business_head | TRUE | FALSE | FALSE | 50 %
Purchse Order Release | 24 | business_head | TRUE | FALSE | FALSE | 50 %
Upload PI | 48 | business_head | TRUE | FALSE | FALSE | 50 %
Payment Request | 24 | business_head | TRUE | FALSE | FALSE | 50 %
Payment Release | 24 | business_head | TRUE | FALSE | FALSE | 50 %