## Sheet1
Sr No | Description | TAT | Action Point | Process Owner | Previous Dependency | Remarks
1 | Initial Design and BOQ Submission | 0 | Designer | Community Manager |  | Start of the Project
2 | Initial Design Approval |  | Customer | Community Manager | 1 | Will not add to the timeline of the project
3 | Revised Design and BOQ Submission | 3 | Designer | Community Manager | 2
4 | 10% Credit |  | Customer | Community Manager | 3
5 | Site Measurement and Site Drawing Submission | 3 | Site Supervisor | Community Manager | 4
6 | Final Design and BOQ Submission | 7 | Designer | Community Manager | 5
7 | CM Approval | 1 | Community Manager | General Manager | 6
8 | 40% Credit |  | Customer | Community Manager | 7
9 | Submission of Production Drawings | 2 | Community Manager | General Manager | 8
10 | Preproduction Site Check | 2 | Site Supervisor | Community Manager | 9
11 | Release of PO | 4 | Category |  | 10
12 | Advance Release to Vendors | 2 | Finance |  | 11
13 | Production | 15 | Category |  | 12
14 | Pre Dispatch Inspection | 2 | Category |  | 13
15 | Site Readiness Check | 2 | Site Supervisor | Community Manager | 13
16 | 50% Credit |  | Customer | Community Manager | 13
17 | Delivery to Site | 6 | Logistics | Category | 13,14,15,16
18 | Installation | 3 | Site Supervisor | Community Manager | 17
19 | Snag Repairs | 8 | Site Supervisor / Designer | Community Manager | 18
20 | Snag Checking | 1 | Site Supervisor / Designer | Community Manager | 19
21 | Buffer | 10 |  |  | 20
22 | Handover | 1 | Site Supervisor / Designer / Community Manager | Community Manager | 21